## Sheet1
|  | Server - :4400 | http://123.34.34.34:8080
| 1 | Set up a server | Server listens to some port number - 4400 | Done
| 2 | Create a sample JSON data | Use data from - https://jsonplaceholder.typicode.com/albums/1/photos | Done
| 3 | /photosapi | Return a JSON of all the photos | Done
| 4 | /photosapi/:id | Return the object of photo of :id | Done
| 5 | Test the API Endpoints | API testing tool should return data | Done
|  | Connect Server to DB |  | Done
|  | /employeesapi | This should read the employees data from the Database | Done
|  | Test localhost:4400/employeesapi | This should return the employees table data in a json format | Done
|  | Client - :4200 | http://133.56.34.234:1234 -> mypage.com/myapp
| 1 | Set up Angular client | ng new... | Done
| 2 | Create photosComponent |  | Done
| 3 | Create photoDetailsComponent |  | Done
| 4 | Routing | Two routes: 1. /photos -> photosComponent 2. /photos/:id -> photoDetailsComponent | Done
| 5 | Router outlet | set router-outlet in app.component.html | Done
| 6 | Test the URLs | Make sure 1. :4200/photos - displays a HTML page 2. :4200/photos/1 - displays a HTML page | Done
| 6.a | Design the UI | Desing UI with dummy data | Done
| 7 | Services - PhotoService | 1. Import { HTTPClientModule} at the app.module 2. Import { HTTPClient } at the service OBSERVABLE (Service is in between the Client and the Server. The client never talks to the server directly. THe service in between managees the communication between the client and the server) | done
| 8 | Subscribe to the Observable | 1. PhotosComponent -> subscribe to /photosapi 2. PhotosDetailsCompoent -> subscribe to /photosapi/:id | done
| 9 | Display Data | Binding -> to display photos | done
|  | Create a new Component called Employees |  | done
|  | Routing | /employees | done
|  | Test the URL | localhost:4200/employees -> Employees Works! | done
|  | Create a dummy JSON data | ID, Emp_name, City_name, Country_name
|  | Bind this data to the UI | *ngFor to bind it
|  | Database: 8889 | http://23.34.23.35:8888
1
| Create | POST | INSERT INTO tbl
| Read | GET | GET data -> Select * from tbl (optionally GET can take a URL param to the server)
| Update | PUT | UPDATE tbl WHERE id=:id
| Delete | DELETE | DELETE FRO tbl
Authentication and Security
Login
DB | 1 | Create a DB for users and populated with users
DB | 2 | Created SP for users to authenticate log in | SP would require an email and password to authenticate
SERVER | 1 | Designed an API Endpoint | http://localhost:4400/login { email: "asdfasdf", password: "asdfasf" }
SERVER | 2 | Created the API in server.js | server.post - call the SP, provide the email and password that the client sent
It will return error or data. If error send the error back to the client
If data, calculate the length of data. If 0, then login failed. Else login successful
Test the API endpoint using REST Client
CLIENT | 1 | Created a component for login
| 2 | Set a path in the router
| 3 | Created a HTML frontend for login using Bootstrap
| 4 | Two-way bound the email and password using ngModule | Imported FormsModule in app.module and registered it in imports
| 5 | Created a Common Service | Imported HTTPClient, created a property of type HTTPClient
| 6 | Create a new method for sending a post request to the API end point | It will require an email and password to be sent along with the request
| 7 | Component has a login method that subscribes to the login Service | It will pass the email and password to the service.
| 8 | Based on the success/failure of authentication | If true, then redirect to another page. IF failed, then display a message to the user
If user registration successful, then provide a link to Log in with the same credentials that the user registerd with
Update User Profile
1 |  | Display a form pre-filled with my details | HTML page with two input boxes - email and password. - Get user details from database based on the userid - localstorage would contain the id of the user | cookies localstorage
Send a PUT request to update the modified values
1. Create a Stored Procedure and test it. analyze the output from the database
2. Create an API Endpoint and test it.
3. Service at the client side to fire the API
4. Pass the data from the front-end to the service and subscribe
5. Update front-end accordingly

## Sheet2
| Server set up | Done
| DB set up | Done
Stored Procedures
| GetPosts() | Done
| NewPost(newPost) | Done
| UpdatePost(:id, updatedPost) | Done
| DeletePost(:id) | Done
API Endpoints
GET | /posts | Done
POST | /posts { post: "asdfasdf" }
UPDATE | /posts/ { id: 5, updatePost: "asdfasdf"}
DELETE | /posts/:id